**Initiative:** Reduce CDI’s by 15% by December 31, 2016 **Intervention:** Isolation Precautions Signage

**Smallest Change:** One room **Scope:** All staff entering patient rooms on the Med/Surg Unit **Total # of Staff Impacted:**

**Planned Testing Timeframe:** 5/31/2016 **Total # of Staff to Test:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Test Description** | **Test Plan** | **Testers** | **Lesson(s) Learned** | **Decision** | **Adaptation** |
| **1** | Standardize precautions signage locations, test one room at a time | Testing to be completed May 26th. | Staff accessing patient rooms 101, 102, 103 | Signage too large and didn’t stick to the wall | Adapt Adopt Abandon | Reduce size of signage, place in same area. |
| **2** | Test newly sized signage | Testing to occur May 28th. | Staff accessing patient rooms 101, 102, 103 | Signage size seems ok, but need better placement area | Adapt Adopt Abandon | Add magnet to signage and place on doorframe |
| **3** | Test new signage in new placement area | Testing to occur May 29th | Staff accessing patient rooms 101, 102, 103 | Signage needs to be a little larger and posted in a plastic sign holder | Adapt Adopt Abandon | Modify size of signage, place in plastic holder |
| **4** | Testing the new signage in plastic holder | Testing to occur May 30th | Staff accessing patient rooms 101, 102, 103 | Positive feedback from staff on new signage and placement location | Adapt Adopt Abandon | Create additional signage for patient rooms and test in all applicable rooms. |
| **5** | Testing of new signage in plastic holder for all applicable patients | Testing to occur May 31st | Staff accessing patient rooms 101, 104, 105, 108 | Positive feedback from staff on all shifts | Adapt Adopt Abandon | Staff education on new signage – staff meetings, huddles, etc. |

This material was prepared in part by the Lake Superior Quality Innovation Network, under contract with the Centers for Medicare & Medicaid Services (CMS), an agency of the U.S. Department of Health and Human Services. The materials do not necessarily reflect CMS policy. 11SOW-WI-C1-15-117 111915